## Issues
Jinkies - Issue Tracker
Generated 2026-03-09 ¦ 68 total issues
24 | 44 | 0 | 6 | 18 | 64.71%
Open | Closed | P1 Open | P2 Open | P3 Open | Completion
# | Priority | Title | Labels | Status | Created | Closed
5 | P0 | HTTP Basic auth credentials stored in plaintext JSON | bug, security | CLOSED | 2026-02-23 | 2026-02-23
17 | P0 | Basic auth credentials sent over plain HTTP | bug, security, feed-poller | CLOSED | 2026-02-23 | 2026-02-23
19 | P0 | file:// URLs not blocked — local filesystem readable via feed config | bug, security, feed-poller | CLOSED | 2026-02-23 | 2026-02-23
91 | P0 | Implement Smarter CI, Increase testing scope and efficacy. Reduce unnecessary CI load. | enhancement, ci | CLOSED | 2026-03-03 | 2026-03-03
98 | P0 | Fix CI YAML and Create CI Tests to verify changes | bug, ci | CLOSED | 2026-03-03 | 2026-03-03
4 | P1 | Lint and tests are not actually executed in the build workflow | bug, ci | CLOSED | 2026-02-23 | 2026-02-24
10 | P1 | Replace bare except in feed poller with specific exception types | bug, feed-poller | CLOSED | 2026-02-23 | 2026-03-09
14 | P1 | Single-instance lock has a TOCTOU race condition | bug, app | CLOSED | 2026-02-23 | 2026-03-09
15 | P1 | Entry ID collision: entries without id/link all get empty-string key | bug, feed-poller | CLOSED | 2026-02-23 | 2026-03-09
26 | P1 | _read_json crashes on corrupted JSON — no JSONDecodeError handling | bug | CLOSED | 2026-02-23 | 2026-03-09
27 | P1 | FeedPoller.update_feeds replaces feed list mid-iteration — thread safety issue | bug, feed-poller | CLOSED | 2026-02-23 | 2026-02-26
34 | P1 | QDesktopServices.openUrl has no URL scheme validation — javascript:/file:/data: links possible | security, dashboard | CLOSED | 2026-02-23 | 2026-02-27
35 | P1 | OPML import does not validate xmlUrl scheme — file:// URLs pass through | security | CLOSED | 2026-02-23 | 2026-03-09
36 | P1 | feedparser.parse (non-auth path) has no timeout — can hang indefinitely | bug, feed-poller | CLOSED | 2026-02-23 | 2026-03-09
42 | P1 | OPML import uses stdlib xml.etree — vulnerable to XXE attacks | security | CLOSED | 2026-02-23 | 2026-03-09
52 | P1 | CI: Qt tests need virtual display (QT_QPA_PLATFORM=offscreen or xvfb) | ci | CLOSED | 2026-02-23 | 2026-02-25
56 | P1 | Add LICENSE file to the repository | documentation | CLOSED | 2026-02-23 | 2026-02-24
8 | P2 | Feed poller should use exponential backoff for transient network failures | enhancement, feed-poller | OPEN | 2026-02-23
9 | P2 | Validate feed URL before saving to config | enhancement, feed-poller, settings | CLOSED | 2026-02-23 | 2026-03-03
16 | P2 | Seen state not persisted to disk on entry click | bug, dashboard | CLOSED | 2026-02-23 | 2026-03-03
18 | P2 | state.json written non-atomically — can corrupt on crash | bug, settings | CLOSED | 2026-02-23 | 2026-02-26
24 | P2 | macOS CI build fails: hdiutil create Resource busy during DMG creation | bug, ci | CLOSED | 2026-02-23 | 2026-02-23
28 | P2 | No confirmation dialog before removing a feed | enhancement, ui | CLOSED | 2026-02-23 | 2026-03-03
29 | P2 | _on_remove_feed reaches into dashboard private widget — broken encapsulation | bug, dashboard | CLOSED | 2026-02-23 | 2026-03-03
30 | P2 | SettingsDialog._import_feeds silently swallows ValueError | bug, settings | CLOSED | 2026-02-23 | 2026-03-03
31 | P2 | Dashboard entries not persisted — empty dashboard on every restart | enhancement, dashboard | CLOSED | 2026-02-23 | 2026-02-25
38 | P2 | App can exit uncleanly if poller is blocked in network request during shutdown | bug, app | CLOSED | 2026-02-23 | 2026-03-03
39 | P2 | reset_daily_stats is defined but never called — daily counters never reset | bug, dashboard | CLOSED | 2026-02-23 | 2026-03-03
40 | P2 | AppConfig.from_dict does not validate notification_style or poll_interval_secs | bug | CLOSED | 2026-02-23 | 2026-03-03
44 | P2 | Dashboard entries list grows unboundedly in memory | enhancement, dashboard | CLOSED | 2026-02-23 | 2026-03-03
45 | P2 | seen_ids set grows unboundedly in memory and on disk | enhancement | OPEN | 2026-02-23
46 | P2 | Feed poller does not use ETag/Last-Modified — full download every cycle | enhancement, feed-poller | OPEN | 2026-02-23
47 | P2 | Add tests for SettingsDialog | testing, settings | OPEN | 2026-02-23
48 | P2 | Add tests for authenticated feed fetching (urllib path) | help wanted, good first issue, testing, feed-poller | OPEN | 2026-02-23
53 | P2 | Windows and macOS builds skip lint and tests entirely | ci | OPEN | 2026-02-23
54 | P2 | macOS build produces bare binary instead of .app bundle in DMG | bug, ci | CLOSED | 2026-02-23 | 2026-03-03
55 | P2 | .gitignore excludes all *.lock files — may prevent uv.lock from being committed | chore | CLOSED | 2026-02-23 | 2026-03-03
58 | P2 | Add SECURITY.md with responsible disclosure process | documentation, security | CLOSED | 2026-02-23 | 2026-03-09
60 | P2 | Linux .desktop entry missing Icon= and StartupWMClass= fields | bug, ui | CLOSED | 2026-02-23 | 2026-03-03
61 | P2 | Add Windows installer (NSIS/Inno Setup) instead of raw .exe | enhancement, Windows | CLOSED | 2026-02-23 | 2026-03-03
66 | P2 | FeedEditDialog accepts blank name and URL with no validation | bug, settings | CLOSED | 2026-02-23 | 2026-03-03
69 | P2 | Error notifications not rate-limited — fires every poll cycle for broken feeds | enhancement, app | CLOSED | 2026-02-23 | 2026-03-03
1 | P3 | Windows is missing a system tray icon | bug, good first issue, Windows | OPEN | 2026-02-20
2 | P3 | Windows uses default pyinstaller app icon | good first issue, Windows, visual | OPEN | 2026-02-20
6 | P3 | JinkiesApp (app.py) has zero test coverage | enhancement, testing | OPEN | 2026-02-23
7 | P3 | Add integration tests for the full polling → notification pipeline | enhancement, testing | OPEN | 2026-02-23
11 | P3 | Entry table needs pagination for feeds with large entry counts | enhancement, dashboard, ui | OPEN | 2026-02-23
12 | P3 | Add bulk mark-as-seen action to the dashboard | enhancement, dashboard, ui | OPEN | 2026-02-23
13 | P3 | Add entry content search and filter to the dashboard | enhancement, dashboard, ui | OPEN | 2026-02-23
32 | P3 | Poll interval change only takes effect after current sleep finishes | bug, feed-poller | OPEN | 2026-02-23
33 | P3 | NotificationDialog._active_notifications is a shared class-level mutable list | bug | OPEN | 2026-02-23
37 | P3 | feed.last_poll_time mutated from poller thread without synchronization | bug, feed-poller | OPEN | 2026-02-23
41 | P3 | Feed.sound_file model field exists but is never used by AudioPlayer | enhancement | OPEN | 2026-02-23
43 | P3 | _refresh_table rebuilds entire table on every poll — O(n) per cycle | enhancement, dashboard | OPEN | 2026-02-23
49 | P3 | Add tests for get_config_dir platform-specific paths | testing | OPEN | 2026-02-23
50 | P3 | Add tests for feed_import edge cases (_build_feed_url, _extract_job_feeds) | testing | OPEN | 2026-02-23
51 | P3 | Add tests for NotificationDialog positioning and lifecycle | testing | OPEN | 2026-02-23
57 | P3 | Add CHANGELOG.md for structured release notes | documentation | CLOSED | 2026-02-23 | 2026-03-09
59 | P3 | README missing config.json structure documentation | documentation | CLOSED | 2026-02-23 | 2026-03-03
62 | P3 | Add an About dialog showing version, license, and links | enhancement, ui | OPEN | 2026-02-23
63 | P3 | Add keyboard shortcuts for toolbar and tray actions | enhancement, ui | OPEN | 2026-02-23
64 | P3 | Add tooltips to toolbar actions for accessibility | enhancement, ui | OPEN | 2026-02-23
65 | P3 | Remove dead code: get_last_poll_display method | good first issue, chore | CLOSED | 2026-02-23 | 2026-03-09
67 | P3 | Remove deprecated block_cipher from jinkies.spec | good first issue, chore | CLOSED | 2026-02-23 | 2026-03-09
68 | P3 | Expose __version__ at runtime from pyproject.toml | enhancement, good first issue | CLOSED | 2026-02-23 | 2026-03-09
70 | P3 | Move inline imports in SettingsDialog to module top level | good first issue, chore | CLOSED | 2026-02-23 | 2026-03-09
100 | none | <Short description of the problem> | bug | CLOSED | 2026-03-03 | 2026-03-03
102 | none | CI Failure with TestDashbaord | bug | CLOSED | 2026-03-03 | 2026-03-03

## Burndown
Burndown Progress
Category | Total | Open | Closed | % Done
P1 - Critical | 12 | 0 | 12 | 100%
P2 - High | 25 | 6 | 19 | 76%
P3 - Low | 24 | 18 | 6 | 25%
All Issues | 68 | 24 | 44 | 64.71%

## By Label
Issues by Label
Label | Total | Open | Closed | % Done
bug | 28 | 4 | 24 | 85.71%
enhancement | 21 | 13 | 8 | 38.1%
feed-poller | 12 | 5 | 7 | 58.33%
dashboard | 10 | 4 | 6 | 60%
ui | 8 | 6 | 2 | 25%
security | 7 | 0 | 7 | 100%
ci | 7 | 1 | 6 | 85.71%
testing | 7 | 7 | 0 | 0%
good first issue | 7 | 3 | 4 | 57.14%
settings | 5 | 1 | 4 | 80%
documentation | 4 | 0 | 4 | 100%
chore | 4 | 0 | 4 | 100%
app | 3 | 0 | 3 | 100%
Windows | 3 | 2 | 1 | 33.33%
help wanted | 1 | 1 | 0 | 0%
visual | 1 | 1 | 0 | 0%